DEPI  |  DATA ANALYSIS TRACK

Project Planning & Management

Project proposal, schedule, task assignment, risk assessment, and KPIs

Air Quality and Life Expectancy: Exploring the Relationship Between Air Pollution and Population Health

## Team Members

Ganat Saad Abdullah Hussein Ahmed  |  Team Leader

Shaimaa Maghraby Mohamed Houssien Elagouz

Habiba Maged Abdel Baqi

Dina Farag Mohamed Mohamed

Nada Ramzy Mohamed Ghnam

Prepared: 15 October 2026  |  Final project target: 30 November 2026

# 1. Project Proposal

## 1.1 Project Overview

This project explores associations between city-level ambient particulate matter (PM2.5 and PM10) and country-year population-health indicators. It combines the WHO Ambient Air Quality Database 2018-version workbook with the Global Health Development Indicators 2000–2023 dataset. The health file supplies life expectancy and supporting demographic, economic, education, sanitation, and health indicators. The project is exploratory and observational; it will describe patterns in matched records rather than claim that air pollution caused a health outcome.

## 1.2 Problem Statement

The source files differ in geographic level and coverage: air-quality values are city-year observations, while health indicators are country-year observations. Air-quality fields also include measured and converted values, uneven temporal coverage, and incomplete metadata. The team must retain source values, create documented numeric fields, aggregate city observations to country-year summaries, match by ISO3 country code and year, and evaluate how coverage and conversion status affect the findings.

## 1.3 Project Objectives

Profile both workbooks and create a data dictionary describing each field, unit where known, type, missingness, and intended use.

Clean and standardize the two sources while preserving raw values and documenting every transformation.

Aggregate city-level PM2.5 and PM10 observations to country-year summaries, retaining city counts and measured/converted counts.

Merge air-quality summaries with health indicators using ISO3 code and year; validate duplicates, unmatched records, and row counts.

Explore relationships between particulate matter and life expectancy, infant mortality, and under-five mortality; use other health and socioeconomic variables as context where appropriate.

Compare patterns across years, regions, and income groups where coverage supports meaningful comparison.

Communicate results in a Power BI dashboard with visible coverage, data-quality notes, and cautious interpretation.

## 1.4 Research Questions and Scope

Across matched country-year records, how are PM2.5 and PM10 associated with life expectancy?

Are higher PM2.5/PM10 values associated with higher infant or under-five mortality in the matched sample?

Do observed patterns differ across regions or income groups?

How do GDP per capita, health expenditure, schooling, water, and sanitation indicators relate to life expectancy, and do they help contextualize the pollution-health patterns?

How much of the result depends on using converted versus measured-only pollution values?

How complete and representative is the matched country-year sample, including the number of cities contributing to each pollution average?

Scope limitation: the air-quality source represents available city measurements, not complete national exposure. A simple mean across available city means is an unweighted descriptive summary, not a population-weighted national exposure estimate. The team will not infer causation from correlation.

## 1.5 Source Datasets and Verified Structure

| Dataset | Verified profile from supplied workbook | Key fields / handling |
| --- | --- | --- |
| Global Health Development Indicators 2000–2023 (Kaggle) | 5,208 rows; 25 columns; 217 countries/entities; 2000–2023. No duplicate ISO3-year keys found; life_expectancy has no missing values in this file. | country, iso3_code, year, region, income_group, life_expectancy, infant_mortality, under_five_mortality, population, gdp_per_capita, health expenditure, immunization, water/sanitation, secondary_school_enrolment. |
| WHO Ambient Air Quality Database 2018-version workbook | 11,962 rows; 15 columns; 108 countries; 4,468 cities; 2008–2017. No duplicate ISO3-city-year keys found. | Country/iso3, City, Year, Annual.mean (PM10), Annual mean, ug/m3 (PM2.5), temporal coverage, conversion flags, station details and source reference. |
| Initial join feasibility | 108 ISO3 codes overlap. Air source has 374 distinct ISO3-year combinations; all 374 keys are present in the health file. Common years are 2008–2017. | After aggregation, validate exact merge counts and keep only matched country-year records for joint analysis. Counts may change for pollutant-specific measured-only analyses. |

## 1.6 Tools and Methods

Excel: source inspection, data dictionary, formulas, quality checks, documented cleaning log, and initial PivotTables.

Power Query: repeatable data-type conversion, status normalization, grouping city records by ISO3 and year, and merging the health table.

Power BI: dashboard visuals, slicers, drill-through, and coverage indicators.

SQL: optional validation queries and grouped summaries if used by the team.

Methods: descriptive statistics, annual trend summaries, scatter plots, correlation, group comparisons, and measured-only sensitivity checks.

# 2. Project Plan & Schedule

The proposed schedule targets final project completion by 30 November 2026. The first-submission documentation deadline is 16 October 2026.

| Task / Phase | Start | Finish | Duration | Main output |
| --- | --- | --- | --- | --- |
| Review dataset structure and quality | 15 Oct 2026 | 19 Oct 2026 | 5 days | Data dictionary and coverage/missingness checks |
| Clean and standardize source files | 20 Oct 2026 | 27 Oct 2026 | 8 days | Clean fields, conversion notes, country-name mapping |
| Aggregate air quality and merge | 28 Oct 2026 | 3 Nov 2026 | 7 days | Country-year table and merge checks |
| Exploratory analysis and KPI calculations | 4 Nov 2026 | 10 Nov 2026 | 7 days | Summary tables and descriptive analysis |
| Excel/SQL analysis and validation | 11 Nov 2026 | 16 Nov 2026 | 6 days | Analysis workbook/queries and validation |
| Build Power BI dashboard | 17 Nov 2026 | 23 Nov 2026 | 7 days | Dashboard with relevant filters |
| Review results and limitations | 24 Nov 2026 | 26 Nov 2026 | 3 days | Checked results and documented limitations |
| Documentation and final presentation | 27 Nov 2026 | 30 Nov 2026 | 4 days | Final report, presentation, and deliverables |

# 3. Task Assignment & Roles

| Role / member | Primary responsibility | Tasks / deliverables |
| --- | --- | --- |
| Role 1 — Ganat Saad Abdullah Hussein Ahmed | Team Leader, Project Coordinator & Excel Data Preparation Analyst | Coordinate project activities, organize tasks, and monitor the project schedule; maintain project documentation; inspect the source datasets in Excel; check missing values, duplicates, inconsistent country names, and other data-quality issues; help define analytical questions and review the team's outputs. |
| Role 2 — Habiba Maged Abdel Baqi | Data Transformation & Integration Analyst | Build repeatable Power Query transformations; standardize fields and identifiers; aggregate city-year records to ISO3-year; merge health indicators; validate merge keys and output grain. |
| Role 3 — Shaimaa Maghraby Mohamed Houssien Elagouz | Exploratory Data Analysis (EDA) Analyst | Perform descriptive analysis of PM2.5, PM10, life expectancy, and adult mortality; explore trends and potential associations in matched records; compare countries and years where data are available; identify patterns, unusual values, and limitations. |
| Role 4 — Dina Farag Mohamed Mohamed | Data Visualization & Dashboard Analyst | Develop suitable charts and the Power BI dashboard; visualize trends, comparisons, and potential relationships; check that visuals accurately represent the validated data; coordinate with the EDA role to ensure visualizations address the project questions. |
| Role 5 — Nada Ramzy Mohamed Ghnam | Research, Reporting & Presentation Analyst; participates in dashboard development | Review credible sources and maintain references; summarize how sources inform project variables and interpretation; contribute to interpreting results with the team; help organize the final project report and presentation materials; participate in developing and reviewing the Power BI dashboard and its visuals. |

# 5. Risk Assessment & Mitigation

| Risk | Why it matters | Mitigation |
| --- | --- | --- |
| Converted pollution values treated as direct measurements | Can bias averages and correlation. | Preserve raw values and conversion flags; show all-values and measured-only sensitivity results when sample size permits. |
| City average interpreted as national exposure | Cities and monitoring coverage are uneven. | Label as average of available city records; show number of cities; avoid national exposure claims. |
| Country/year join mistakes | Can pair health values with wrong pollution records. | Join on ISO3 plus year; validate one health row per key; compare row counts before/after merge. |
| Missing socioeconomic fields | Can reduce usable rows for secondary analyses. | Calculate valid-pair counts per analysis; do not impute without a justified rule. |
| Overinterpretation of correlation | Confounding factors are not fully controlled. | Use “associated with”; discuss population, economic, health and monitoring differences. |
| Schedule or role overlap | Can cause duplicated work and missed handoffs. | Use shared task tracker, named owners, deadlines and agreed deliverable formats. |

# 6. Project KPIs

| KPI | Definition / calculation | Importance |
| --- | --- | --- |
| Average PM2.5 (µg/m³) | Mean of valid PM2.5 observations within each country-year after documented cleaning. | Main fine-particle pollution measure. |
| Average PM10 (µg/m³) | Mean of valid PM10 observations within each country-year after documented cleaning. | Second particulate-matter measure for comparison. |
| Life expectancy (years) | Life-expectancy value from the source dataset for each matched country-year. | Primary population-health outcome. |
| Adult Mortality | Adult Mortality value as defined in the source dataset. | Secondary health outcome; interpret using source definition and units. |
| City coverage count | Number of distinct cities contributing valid observations to each country-year pollutant average. | Shows the amount of city-level information supporting each average. |
| Matched country-year count | Number of unique country-year keys present in both prepared datasets. | Measures the final integration coverage and analytical sample size. |
| Data completeness (%) | Non-missing valid values divided by expected values, multiplied by 100, calculated for key fields. | Shows how much of the required data is available. |
| Pollution-health correlation | Pearson correlation between a pollutant measure and a health outcome using valid matched pairs. | Summarizes direction and strength of linear association; it does not establish causation. |

# 7. Sources

Health dataset (Kaggle): https://www.kaggle.com/datasets/roccot/global-health-development-indicators-2000-2023

Air-quality dataset (Kaggle): https://www.kaggle.com/datasets/fkosmowski/ambient-air-quality-database

WHO 2018 database summary: https://cdn.who.int/media/docs/default-source/air-quality-database/aqd-2018/aap_database_summary_results_2018_final2.pdf

WHO explains that its air-quality database contains city/town annual means, uneven coverage, and some converted values; this supports the project’s coverage and conversion cautions.